## Tasklists
Task ID | Task list | Milestone | Task name | Task description | Start date | Due date | Priority | Private | Progress | Status | Status text | Assigned to | Date created | Created by firstname | Created by lastname | Completed date | Completed by firstname | Completed by lastname | Parent task | Completed on time | Priority text | Tags | Board column
664893 | Software Design Report | CW1 Software Design | Project background and rational |  | 2022-09-29 | 2022-10-13 |  | 0 | 30 | new | started | Derek Peacock | 2022-09-10 16:26 | Derek | Peacock |  |  |  |  | FALSE | No priority | Doc | Completed
664902 | Software Design Report | CW1 Software Design | Feature List |  | 2022-09-29 | 2022-10-06 |  | 0 | 0 | reopened | not started | Anyone | 2022-09-10 16:31 | Derek | Peacock |  |  |  |  | FALSE | No priority | Doc | To do
818099 | Software Design Report | CW1 Software Design | Feature List --> First Draft Feature List |  | 2022-09-29 | 2022-10-06 |  | 0 | 0 | new | not started | Anyone | 2022-09-15 19:57 | Derek | Peacock |  |  |  | 664902 | FALSE | No priority | Draft
818100 | Software Design Report | CW1 Software Design | Feature List --> Reviewed Feature List |  | 2022-09-29 | 2022-10-06 |  | 0 | 0 | new | not started | Anyone | 2022-09-15 19:58 | Derek | Peacock |  |  |  | 664902 | FALSE | No priority | Review
664895 | Software Design Report | CW1 Software Design | Use Case Diagram |  | 2022-10-10 | 2022-10-14 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:27 | Derek | Peacock |  |  |  |  | FALSE | No priority | UML | To do
664897 | Software Design Report | CW1 Software Design | Use Case Specifications |  | 2022-10-15 | 2022-10-21 |  | 0 | 0 | reopened | not started | Anyone | 2022-09-10 16:27 | Derek | Peacock |  |  |  |  | FALSE | No priority | UML
664898 | Software Design Report | CW1 Software Design | User Interface Designs |  | 2022-10-23 | 2022-10-25 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:29 | Derek | Peacock |  |  |  |  | FALSE | No priority | UML
664899 | Software Design Report | CW1 Software Design | User Stories |  | 2022-10-24 | 2022-10-30 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:30 | Derek | Peacock |  |  |  |  | FALSE | No priority | UML
664900 | Software Design Report | CW1 Software Design | UML Class Diagram |  | 2022-10-31 | 2022-11-08 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:30 | Derek | Peacock |  |  |  |  | FALSE | No priority | UML
664901 | Software Design Report | CW1 Software Design | Database ERD |  | 2022-10-31 | 2022-11-08 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:30 | Derek | Peacock |  |  |  |  | FALSE | No priority | ERD
664929 | Software Implementation | CW2 Software Implementation | Report on ASP.NET Technology |  |  | 2023-01-13 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:43 | Derek | Peacock |  |  |  |  | FALSE | No priority | Doc
664930 | Software Implementation | CW2 Software Implementation | Update Project Background |  |  | 2023-01-13 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:43 | Derek | Peacock |  |  |  |  | FALSE | No priority | Doc
664931 | Software Implementation | CW2 Software Implementation | Update Use Case Diagram |  |  | 2023-01-13 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:43 | Derek | Peacock |  |  |  |  | FALSE | No priority | UML
664932 | Software Implementation | CW2 Software Implementation | Update Class Diagram |  |  | 2023-01-13 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:44 | Derek | Peacock |  |  |  |  | FALSE | No priority | UML
664933 | Software Implementation | CW2 Software Implementation | Update Database ERD |  |  | 2023-01-13 |  | 0 | 0 | new | not started | Anyone | 2022-09-10 16:44 | Derek | Peacock |  |  |  |  | FALSE | No priority | ERD
818094 | Software Implementation | CW2 Software Implementation | Add Models |  | 2022-11-24 | 2023-01-13 |  | 0 | 0 | new | not started | Anyone | 2022-09-15 19:51 | Derek | Peacock |  |  |  |  | FALSE | No priority | C